## INFO
ATLANTIC SALMON RECOVERY WORKPLAN FOR THE DOWNEAST, PENOBSCOT AND MERRYMEETING BAY SHRU
CREATED: 2015
LAST UPDATED: July 2015 By Dan Kircheis
CONTENTS:
1). SHRU LEVEL THREATS AND RECOVERY ACTIVITIES FOR EACH SHRU. THESE DESCRIBE THE BIG PICTURE THREATS FOR EACH OF SHRU'S AND THE TYPES OF ACTIVITIES NEEDED TO ADDRESS THEM
Marine and Estuary threats and recovery activities (non-SHRU specific)
Downeast SHRU level threats and recovery activities
Penobscot SHRU level threats and recovery activities
Merrymeeting Bay SHRU level threats and recovery activities
2). SITE SPECIFIC THREATS AND RECOVERY ACTIVITIES WITHIN EACH SHRU. THESE DESCRIBE VERY SPECIFIC ACTIVITES THAT ARE SEEN AS HIGHEST PRIORITY FOR IMPLEMENTATION EITHER BECAUSE OF THEIR CONSERVATION VALUE TO SALMON OR THEY REPRESENT A NEAR-TERM CONSERVATION OPPORTUNITY THAT SHOULD NOT BE MISSED.
Downeast SHRU site specific threats and recovery activities
Penobscot SHRU site specific threats and recovery activities
Merrymeeting Bay SHRU site specific threats and recovery activities

## Marine and Estuary
SITE SPECIFIC THREATS | SUB-BASIN | WATERSHED | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES | DATE LISTED | STATUS/ DATE COMPLETED | RECOVERY ACTION IN THE RECOVERY PLAN THAT THE ACTIVITY ADDRESSES
Coastal development - dredging, offshore renewable energy, etc. | Estuary/Bay | Estuary/Bay | ME1.0 | Work with industury to ensure any projects (test or otherwise), construction, or infrastructure will not interfere with ATS migration or create the potential for take. | ME1.1 | MEAT | NMFS | 2015
Resuspending sawdust/wood chips - increased turbidity in the Franklin Flats area of the Penobscot River. | Estuary/Bay | Penobscot | ME2.0 | Study the chemical-physical interactions and assess the feasiblilty of removing relict sawdust/wood chip deposits that increase turbidity. | ME2.1 | MEAT | NMFS | 2015
Changing suite of predators (i.e.cormorants, seals) for migrating ATS to adapt to. | Estuary/Bay | Estuary/Bay | ME3.0 | Investigate both lethal and non-lethal mechanisms to reduce predation on juvenile and adult ATS. | ME3.1 | MEAT | NMFS | 2015
|  |  |  | Minimize predation risks estuary and coastal through habitat improvement and ecosystem management/restoration including restoration of co-evolved species. | ME3.2 | MEAT | NMFS | 2015
|  |  |  | Identify ways to manage predation on Atlantic salmon through habitat, ecosystem, and predator management | ME3.3 | MEAT | NMFS | 2015
Remnant obsolete structures (i.e. wooden piers, cribworks) that provide artificial habitat for potential predators. | Estuary/Bay | Estuary/Bay | ME4.0 | Evaluate feasibility of removing obsolete structures with no historical or aesthetic value. | ME4.1 | MEAT | NMFS | 2015
Temperature shift between fresh water and saline environment. | Estuary/Bay | Estuary/Bay | ME5.0 | Engage in conversations with hydro to ensure flow regimes and head pond temperatures are adequate for ATS emigration as well as adult migration to natal spawning grounds. | ME5.1 | MEAT | NMFS, USGS | 2015
Directed domestic catch in state and federal waters. | US Waters | US Waters | ME6.0 | Prohibit directed take of Atlantic salmon in estuary and marine state waters by maintaining protections in ATS FMP. | ME6.1 | MEAT | DMR | 2015
Bycatch in other state and federal fisheries. | US Waters | US Waters | ME7.0 | Monitor bycatch annually through NMFS observer programs and report out totals in USASAC working paper. If issues are idenitfied, update relevent FMPs to reduce bycatch. | ME7.1 | MEAT | NMFS | 2015
Low estuary and Marine Survival | Estuary/Bay | Estuary/Bay | ME8.0 | Integrate recent estuary-coastal salmon science findings into operational fish and habitat management activities while continuing studies to better understand the location and mechanisms of estuarine-coastal mortality. | ME8.1 | MEAT | NMFS, USGS | 2015
|  |  |  | Monitor how changes in fish communities impact salmon survival and foster any possitive changes observed through comprehensive ecosystem management | ME8.2 | MEAT | NMFS | 2015
|  |  |  | Refine our understanding of core factors influencing survival and in the near future to identify and implement adaptive management strategies to reduce these losses. | ME8.3 | MEAT | NMFS | 2015
|  |  |  | Optimize stocking to improve estuary transition survival for hatchery smolts | ME8.4 | MEAT | NMFS | 2015
Recent work by Mills et al. (2014) and Renkawitz et al. (in review) suggests impacts on capelin resulting from climate-driven ecosystem changes could be translating into less abundant and lower quality salmon forage. | Distant Water Feeding Grounds | North Atlantic | ME9.0 | Engage with international partners in comprehensive management solutions at broad spatial scales | ME9.1 | MEAT | NMFS | 2015

## Pen SHRU Threats
PENOBSCOT SHRU OVERARCHING THREATS AND RECOVERY ACTIONS
OVERARCHING THREATS WITHIN THE PENOBSCOT SHRU | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES
Climate change has, and will likely continue to change the spatial landscape of habitats most suitable for Atlantic salmon. Throughout the basin there are areas that may be more vulnerable to climate change and may become less suitable for Atlantic salmon, while other areas may be more resilient and warrant greater protection. | PBS1.0 | Remove all fish passage impediments (dams, culverts, remnant dams) to allow salmon to find and use areas of cold water refuge on timescales that they deem necessary. | PBS1.1 | CAT | NGO's, DOT, Municipalities, PIN, Owners of dams and culverts
|  | Identify and protect habitat areas throughout the basin that may have higher resilience to climate change, particularly warming | PBS1.2 | FWAT | USFWS, MEDMR, PIN
|  | Develop outreach material to articulate the impacts of climate change on aquatic ecosystems and the mechanisms to combat it | PBS1.3 | Outreach | NMFS, Sea Grant, USFWS
|  | Evaluate and implement Best Management Practices for agriculture and forest lands that may help offset the effects of warming | PBS1.4 | FWAT | USDA-NRCS, PIN, Maine Forest Service
Dams and culverts are ubiquitous throughout the Penobscot SHRU. Dams and culverts block or impede access to habitats used for spawning and rearing Atlantic salmon; degrade habitat features for native riverine species; alter the biodiversity that native species have adapted to; and block or impair access to lakes and ponds used by many diadromous fish species, particularly alewives that use these areas for feeding, spawning, rearing | PBS2.0 | Seek out opportunities at dams and road crossings throughout the SHRU where access can be improved for diadromous fish, including river herring and Atlantic salmon | PBS2.1 | CAT | NMFS, USFWS, MDMR, PIN, NGO’s
|  | Conduct outreach to educate the public about diadromous fish and their contribution to freshwater ecosystems, and how dams affect them | PBS2.2 | Outreach | NMFS, Sea Grant, NGO’s
|  | Conduct outreach on the tradeoffs that dams provide as a source of green energy vs. their impacts to fisheries. | PBS2.3 | Outreach | USFWS, NMFS, Sea Grant, NGO’s
|  | Conduct outreach on dam and culvert removal projects to educate the public on the value of these efforts | PBS2.4 | Outreach | NMFS, USFWS, UMaine, Sea Grant, NGO’s, Maine Audobon
|  | Remove all fish passage impediments (dams and culverts) to allow salmon to find and use spawning areas on timescales that they deem necessary. | PBS2.5 | CAT | MEDMR, NMFS, USFWS, PIN, NGO's, owners of barriers
|  | Evaluate, through consultation, dam or culvert modification or installation project to assure that projects provide for upstream and downstream passage of all life stages of Atlantic salmon sufficient to sustain recovery. | PBS2.6 | CAT | NOAA, USFWS
|  | Assure that consultations on road crossing projects throughout the Penobscot SHRU result in cumulative gains in habitat that support survival and recovery | PBS2.7 | CAT | NOAA, USFWS
The stocking and introduction of non-native species, particularly smallmouth bass, compete with and prey on Atlantic salmon in the Penobscot SHRU. Headponds associated with dams have degraded habitat features well suited for Atlantic salmon while created habitats particuarly well suited for small mouth bass, subsequently increase predation preasure on juvenile salmon. | PBS3.0 | Assess the impact of non-native species on juvenile salmon, including emigrating smolts and sites where predation occurs most frequently. | PBS3.1 | FWAT | MEDMR, MEDIF&W
|  | Implement fish management activities and regulations that minimizes the spread of invasive species without compromising the recovery of Atlantic salmon and the co-evolved suite of diadromous fish | PBS3.2 | FWAT | MEDMR, MEDIF&W
|  | Conduct outreach on the impacts of invasive species | PBS3.3 | OET | MEDIF&W, MEDMR, USFWS
|  | Implement fish management activities and regulations that help minimize the effects of predation and competition by introduced species | PBS3.4 | FWAT | MEDMR, MEDIF&W
|  | Implement activities that encourage healthy populations of native fish communities and discourage introduced species | PBS3.5 | FWAT | MEDMR, MEDIF&W
Current stocking and broodstock collection practices have homogenized the Penobscot stock of Atlantic salmon and limits local adaptation to variable habitats throughout the basin. | PP4.0 | Develop and implement a stocking and broodstock strategy that promotes local adaption of stocks throughout the Penobscot basin. The strategy should: 1) Preserve and promote the genetic diversity, 2) Prevent the further loss of family groups, 3) allow for marine and freshwater selection to maximize fitness, and 4) account for habitat variability and climate change scenarios | PBS4.1 | GDAT, CHAT | MEDMR, USFWS
Pollution attributed to landuse and development practices in the Penobscot Bay SHRU can harm Atlantic salmon and degrade the productive capacity of freshwater and estuary habitats. Types of pollution from landuse and development practices include: Non-point sources of pollution including nutrient runoff and pesticide contamination of surface waters from forestry, agriculture and residential/commercial land use practices; Increased erosion and radiational warming from clearing lands as a result of forest harvesting, agricultural and residential development; chemical and organic pollutants from storm water runoff, combined sewer over flows, and waste water discharge | PBS5.0 | Implement best management practices in forestry and agricultural practices that minimizes soil erosion, nutrient runoff, and pesticide contamination of surface and ground waters | PBS5.1 | FWAT | EPA, PIN, USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify and implement landuse best management practices that minimizes radiational warming that can elevate surface water temperatures | PBS5.2 | FWAT | PIN, USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Implement best management practices that ensures that storm water runoff, combined sewer overflows and waste water discharges do not harm Atlantic salmon and their habitats | PBS5.3 | FWAT | EPA, PIN, USFWS, NOAA, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Evaluate whether existing state and federal water quality standards are sufficient to allow for survival and recovery. | PBS5.4 | FWAT | EPA, MEDEP, PIN
|  | Evaluate of effects of legacy contaminants in the Penobscot and the extent that it could effect Atlantic slmon survival and recovery | PBS5.5 | FWAT | EPA, MEDEP, PIN
|  | Evaluate the affects of water use on minimum flows in the Penobscot Watershed | PBS5.6 | FWAT | USGS, MEDEP
Historic and current landuse have degrade the complexity and productivity of freshwater habitats that support Atlantic salmon in the Penobscot Bay SHRU. Types of current and historic land use practices include: historic log drives straightened channels and removed wood and boulders in some areas altering stream flow and habitat complexity; past and current agriculture and forestry practices, and residential development practices have reduced the density and age of trees in the riparian area that provides for shade, cover, bank stability and complexity, and nutrient inputs. | PBS6.0 | Develop and implement a plan that ensures land use practices protect riparian zones in a manner that maximizes riparian zone function | PBS6.1 | FWAT | PIN, USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify and implement landuse best management practices that ensures protections of Atlantic salmon and their habitats. | PBS6.2 | FWAT | PIN, USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify, quantify and map river reaches where channel complexity is believe to be most impaired from historic log drive practices. | PBS6.3 | FWAT | PIN, MEDMR
|  | Develop a written strategy to restore identified degraded stream reaches that includes productivity goals, metrics to gauge success, and public education | PBS6.4 | FWAT | PIN, MEDMR
The agencies have limited resources to assess all areas that could be occupied by salmon, and therefor many sites with good habitat are not routinely assessed. It is important for the agencies to know if and when rivers and streams are being used by salmon and if salmon are being held up below barriers to migration (dams and culverts). | PBS7.0 | Monitor rivers and streams that are not frequently monitored by the agencies to look for evidence of salmon occupation. | PBS7.1 | FWAT | NGO's, PIN
|  | Monitor areas below dams and culverts to look for evidence of salmon occupation. | PBS7.2 | CAT | NGO's, PIN

## Pen Site Specific Threats
PENOBSCOT SHRU SITE SPECIFIC THREATS AND RECOVERY ACTIVITIES
SITE SPECIFIC THREATS | SUB-BASIN | WATERSHED | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES | DATE LISTED | STATUS/ DATE COMPLETED | RECOVERY ACTION IN THE RECOVERY PLAN THAT THE ACTIVITY ADDRESSES
The Ducktrap river is believed to have one remaining cohort that is reflected by redds that are documented in the river once every three years. The small number of redds resulting from this single cohort, and given that the Ducktrap stock is not maintained in a pedigree line in a hatchery, puts this stock at extremely high risk of extirpation. | Penobscot River Below Veazie | Ducktrap | P1.0 | Evaluate the genetics of the existing stock for baseline monitoring | P1.1 | GDAT | MEDMR, USFWS | 2015 |  | 2.1, 22
|  |  |  | The Ducktrap is a focus area for proactive efforts to identify and address anthropogenic barriers that block or impair access to migratory fish, including Atlantic salmon | P1.2 | FWAT | NMFS, USFWS | 2015 |  | 1.5, 1.6, 1.7, 1.8, 1.12, 4.4
Marsh Stream has abundant nursery habitats that could support Atlantic salmon but for the Frankfort Dam that continues to significantly delay, and most often blocks passage of Atlantic salmon | Penobscot River Below Veazie | Marsh Stream | P2.0 | Continue to work with the owner of the Frankfort dam and FERC to find solutions to assure survival and recovery of Atlantic salmon | P2.1 | CAT | NMFS, FERC, USFWS | 2015
|  |  |  | Consider enforcement Activitys if necessary | P2.2 | CAT | NMFS, FERC, USFWS | 2015
The Orland River watershed provides considerable opportunities for river herring that are ecologically important to the continued survival of Atlantic salmon, as well as some opportunities for Atlantic salmon spawning and rearing. The Orland River Dam, Alamoosook Lake Dam and the Upper Falls Road culvert may limit passage and survival of river herring and salmon. | Penobscot River Below Veazie | Orland River | P3.0 | Work with the town of Orland to find solutions for the Orland River Dam and Alamoosook dam that assures the survival and recovery of Atlantic salmon and maximizes opportunities for river herring | P3.1 | CAT | NMFS, USFWS, MDOT, MEDMR, Town of Orland | 2015
|  |  |  | Design and implement solutions at the Upper Falls Road culvert that assures the survival and recovery of Atlantic salmon and maximizes opportunities for river herring. | P3.2 | CAT | USFWS, MDOT | 2015
The Kenduskeag Stream has suitable habitats for blueback herring and Atlantic salmon. Adult salmon frequently enter the Kenduskeag during warm summers in search of cooler waters. The site of the old flour mill may block passage of blueback herring and, at times, may delay passage of Atlantic salmon | Penobscot River Below Veazie | Kenduskeag Stream | P4.0 | Survey and assess the site of the old flour mill in Bangor to determine if passage can be improved for the benefit of salmon and blueback herring | P4.1 | CAT | MEDMR, USFWS | 2015
During years that adult salmon hold in the lower Kenduskeag are often subjected to harassment or poaching | Penobscot River Below Veazie | Kenduskeag Stream | P5.0 | Increase outreach and enforcement in the areas below the old flour mill when Atlantic salmon are present | P5.1 | FWAT/Outreach | MEDMR, USFWS | 2015
The Milford, Orono, West Enfield, Stillwater and Weldon dams and their operations can: 1) Block and impede access of Atlantic salmon and co-evolved diadromous species; 2) Directly and indirectly kill or harm Atlantic salmon; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbate the effects of climate change | Mainstem Penobscot River and small tributaries above Veazie | Mainstem Penobscot and Stillwater Rivers | P6.0 | Complete a species protection plan at the Milford dam to establish upstream and downstream fish passage efficiency standards required to ensure the survival and recovery of Atlantic salmon. | P6.1 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
|  |  |  | Complete a species protection plan at the Stillwater dam to establish upstream and downstream fish passage efficiency standards required to ensure the survival and recovery of Atlantic salmon. | P6.2 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
|  |  |  | Complete a species protection plan at the Weldon dam to establish upstream and downstream fish passage efficiency standards required to ensure the survival and recovery of Atlantic salmon. | P6.3 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
|  |  |  | Evaluate and modify operations of Milford as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan. | P6.4 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
|  |  |  | Evaluate and modify operations of Stillwater as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan. | P6.5 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
|  |  |  | Evaluate and modify operations of Weldon as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan. | P6.6 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
High water temperatures in the main stem Penobscot requires that adult and juvenile salmon seek out areas of cool water, including springs and tributary streams. Some of these cool water resources are threatened by development or have limited access because of dams and/or culverts. | Mainstem Penobscot River and small tributaries above Veazie | Mainstem Penobscot River and tributaries | P7.0 | Identify and document sources of cool water that could serve as refuge for adult and juvenile salmon | P7.1 | FWAT | MEDMR, PIN, USFWS | 2015
|  |  |  | Ensure that all areas of cool water along the mainstem Penobscot are protected from Activities that degrade water quality and limit accessibility for both adults and juveniles. | P7.2 | FWAT | NMFS, USFWS, PIN | 2015
Cormorants and introduced smallmouth bass predate on emigrating Atlantic salmon smolts. Opportunities for predation on smolts may be exacerbated during times of smolt stocking and at dams that have artificial lighting | Mainstem Penobscot River and small tributaries above Veazie | Mainstem Penobscot River | P8.0 | Explore alternative stocking strategies, including night stocking, to assess its effectiveness at minimizing predation by diurnal predators. | P8.1 | CHAT | USFWS, MEDMR | 2015
|  |  |  | Assess whether artificial lighting increases opportunities for predation at dams, particularly by cormorants, and implement measures to minimize these impacts | P8.2 | FWAT | MEDMR, PIN, Hydro-developers | 2015
There is a risk that a large number of adult returns will use the Stillwater River over the mainstem Penobscot, and subsequently would be subject to a trap and trucking operation that may not be sufficient to allow for survival and recovery. | Mainstem Penobscot River and small tributaries above Veazie | Stillwater River | P9.0 | Evaluate adult returns and passage delays at the Orono Dam | P9.1 | CAT | Hydro Developers, FERC, NMFS, USFWS | 2015
|  |  |  | Develop contingency measures to address any delays or impacts to adult migration | P9.2 | CAT | Hydro Developers, FERC, NMFS, USFWS, PIN | 2015
The Rt. 178 culvert on Blackman Stream impairs access of alewives to suitable spawning and nursery habitats | Mainstem Penobscot River and small tributaries above Veazie | Blackman Stream | P10.0 | Repair or replace culvert to assure alewives have unimpeded access to spawning and nursery habitats | P10.1 | CAT | MDOT, USFWS, PIN | 2015
The Pumpkin Hill dam and its operations can: 1) Block and impede access of Atlantic salmon and co-evolved diadromous species; 2) Directly and indirectly kill or harm Atlantic salmon; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbate the effects of climate change | Passadumkeag River and its tributaries | Passadumkeag River | P11.0 | Complete a species protection plan and adjust operations at this dam so that it meets or exceeds any upstream and downstream fish passage efficiency standards required to ensure survival and recovery of Atlantic salmon. | P11.1 | CAT | owners and operators of the Pumpkin Hill Dam, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan | P11.2 | CAT | owners and operators of the Pumpkin Hill Dam, FERC, NMFS | 2015
The East Branch of the Mattawamkeag has highly suitable habitats for Atlantic salmon spawning and rearing. Landuse practices, development and road crossings can affect the quality and availability of these habitats | Mattawamkeag River and its tributaries | East Branch Mattawamkeag River and its tributaries | P12.0 | The East Branch Mattawamkeag River and its Tributaries are a focus area for proactive efforts to identify and address anthropogenic barriers including dams and road crossings that block or impair access to migratory fish, including Atlantic salmon | P12.1 | CAT | USFWS, MDOT, Maine Forest Service | 2015
|  |  |  | The East Branch Mattawamkeag and its tributaries are focus areas for proactive efforts to identify and address landuse and development practices that degrade or impair habitat quality and quantity for migratory fish, including Atlantic salmon | P12.2 | FWAT | USFWS, MDOT, , Maine Forest Service | 2015
The rivers and streams within the Mollunkus watershed has recently been identified as possibly providing considerably more opportunities for Atlantic salmon spawning and rearing then was previous understood. | Mattawamkeag River and its tributaries | Mollunkus Stream | P13.0 | Evaluate areas of suitable Atlantic salmon habitats for occupancy, productivity and survival | P13.1 | FWAT | MEDMR | 2015
Currently, the Howland dam can: 1) Block and impede access of Atlantic salmon and co-evolved diadromous species; 2) Directly and indirectly kill or harm Atlantic salmon; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbate the effects of climate change | Piscataquis River and its Tributaries | Piscataquis River | P14.0 | Develop (if not already complete) a species protection plan and adjust operations at this dam such that they meet or exceed any upstream and downstream fish passage efficiency standards required to ensure survival and recovery of Atlantic salmon. | P14.1 | CAT | owners and operators of the dams | 2015
Part of the PRRP is to construct a bypass reach around the Howland Dam as an alternative to its removal. If the bypass reach is constructed, the effectiveness and stability of the bypass reach is uncertain, and may affect Atlantic salmon | Piscataquis River and its Tributaries | Piscataquis River | P15.0 | Monitor the effectiveness of the bypass reach and assure its operations allow for the survival and recovery of Atlantic salmon and co-evolved diadromous species. | P15.1 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Develop a long term maintenance plan and secure funding to support its implementation. | P15.2 | CAT | Owners of the bypass reach | 2015
The Browns Mills, Moosehead, and Sebec Dams and their operations can: 1) Block and impede access of Atlantic salmon and co-evolved diadromous species; 2) Directly and indirectly kill or harm Atlantic salmon; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbate the effects of climate change | Piscataquis River and its Tributaries | Piscataquis River | P16.0 | Develop a species protection plan at the Browns Mills dam such that its opperations meets or exceeds any upstream and downstream fish passage efficiency standards required to ensure survival and recovery of Atlantic salmon. | P16.1 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Develop a species protection plan at the Moosehead dam such that its opperations meets or exceeds any upstream and downstream fish passage efficiency standards required to ensure survival and recovery of Atlantic salmon. | P16.2 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Develop a species protection plan at the Sebec dam such that its opperations meets or exceeds any upstream and downstream fish passage efficiency standards required to ensure survival and recovery of Atlantic salmon. | P16.3 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations at the Browns Mills Dam as needed until operations meet or exceed the specified standards in the SPP. Standards must be met within ten years of the completion of any final species protection plan. | P16.4 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations at the Moosehead Dam as needed until operations meet or exceed the specified standards in the SPP. Standards must be met within ten years of the completion of any final species protection plan. | P16.5 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations at the Sebec Dam as needed until operations meet or exceed the specified standards in the SPP. Standards must be met within ten years of the completion of any final species protection plan. | P16.6 | CAT | owners and operators of the dams, FERC, NMFS | 2015
The Guilford Dam can: 1) Block and impede access of Atlantic salmon and co-evolved diadromous species; 2) Directly and indirectly kill or harm Atlantic salmon; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbate the effects of climate change | Piscataquis River and its Tributaries | Piscataquis River | P17.0 | Conduct feasibility study to examine reasonable and prudent options that ensures survival and recovery of Atlantic salmon and implement the studies recommendations | P17.1 | CAT | owners and operators of the dam, NMFS, MEDMR | 2015
The Piscataquis River watershed above the Guilford Dam has highly suitable, abundant habitats for Atlantic salmon spawning and rearing. Landuse practices, development and road crossings can affect the quality and availability of these habitats | Piscataquis River and its Tributaries | Piscataquis River | P18.0 | The Piscataquis River above Guilford is a focus area for proactive efforts to identify and address anthropogenic barriers including dams and road crossings that block or impair access to migratory fish, including Atlantic salmon | P18.1 | CAT | USFWS, MDOT, PIN, Maine Forest Service | 2015
|  |  |  | The Piscataquis River above Guilford is a focus area for proactive efforts to identify and address landuse and development practices that degrade or impair habitat quality and quantity for migratory fish, including Atlantic salmon | P18.2 | FWAT | USFWS, MDOT, PIN, Maine Forest Service | 2015
Within the Piscataquis sub-basin, Kingsbury Stream has highly suitable, abundant habitats for Atlantic salmon spawning and rearing. Land use practices, development and road crossings can affect the quality and availability of these habitats | Piscataquis River and its Tributaries | Kingsburry Stream | P19.0 | Kingsbury Stream is a focus area for proactive efforts to identify and address anthropogenic barriers including dams and road crossings that block or impair access to migratory fish, including Atlantic salmon | P19.1 | CAT | USFWS, MDOT, Maine Forest Service | 2015
|  |  |  | Kingsbury Stream is a focus area for proactive efforts to identify and address landuse and development practices that degrade or impair habitat quality and quantity for migratory fish, including Atlantic salmon | P19.2 | FWAT | USFWS, MDOT, , Maine Forest Service | 2015
Within the Piscataquis sub-basin, the West Branch Pleasant River above Silver Lake, East Branch Pleasant River, and Middle Branch Pleasant River have highly suitable, abundant habitats for Atlantic salmon spawning and rearing. Land use practices, development and road crossings can affect the quality and availability of these habitats | Piscataquis River and its Tributaries | West Branch, East Branch, and Middle Branch Pleasant River | P20.0 | The West Branch, East Branch and Middle Branch Pleasant are focus areas for proactive efforts to identify and address anthropogenic barriers including dams and road crossings that block or impair access to migratory fish, including Atlantic salmon | P20.1 | CAT | USFWS, MDOT, Maine Forest Service | 2015
|  |  |  | The West Branch, East Branch and Middle Branch Pleasant are focus areas for proactive efforts to identify and address landuse and development practices that degrade or impair habitat quality and quantity for migratory fish, including Atlantic salmon | P20.2 | FWAT | USFWS, MDOT, Maine Forest Service | 2015
Historic log driving practices in the East Branch Penobscot and Sebois River is likely responsible for reducing substrate diversity and may be wholly or partially to blame for these rivers appearing to be over wide and shallow, and subsequently warmer than they would be otherwise. This may be particularly true in the Sebois where temperatures may be limiting juvenile survival. | East Branch Penobscot River | East Branch Penobscot River | P21.0 | Assess the feasibility of conducting a large wood/ boulder project in this region and develop a study design for its implementation | P21.1 | FWAT | MEDR, PIN, USFWS, MEDIFW | 2015
|  |  |  | If its determined to be feasible and appropriate, implement the large wood/boulder project according to the study design. | P21.2 | FWAT | MEDR, PIN, USFWS, MEDIFW | 2015
The West Branch Penobscot River has high quality and abundant habitat features that could support Atlantic salmon spawning and rearing but for dams that precludes access. The West Branch may also be one of the more resilient watersheds in the basin to climate change which would elevate its importance to salmon recovery | West Branch Penobscot River | West Branch Penobscot River | P22.0 | Include the West Branch Penobscot in the basin wide assessment of climate change resilience to determine its importance to Atlantic salmon recovery efforts | P22.1 | FWAT | MEDMR, USFWS | 2015
|  |  |  | Engage in the next round of hydro dam relicensing with owners of dams on the West Branch to determine appropriate Activitys for precluding access to abundant, high quality habitat. | P22.2 | CAT | NMFS | 2015
|  |  |  | Use the West Branch as an incubation stream for juvenile production | P22.3 | FWAT | MEDMR, USFWS | 2015

## MMB SHRU Threats
MERRYMEETING BAY SHRU OVERARCHING THREATS AND RECOVERY ACTIONS
OVERARCHING THREATS WITHIN THE MERRYMEETING BAY SHRU | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES
Climate change has, and will likely continue to change the spatial landscape of habitats most suitable for Atlantic salmon. Throughout the basin there are areas that may be more vulnerable to climate change and may become less suitable for Atlantic salmon, while other areas may be more resilient and warrant greater protection. | MBS1.0 | Remove all fish passage impediments (dams, culverts, remnant dams) to allow salmon to find and use areas of cold water refuge on timescales that they deem necessary. | MBS1.0 | CAT | NGO's, DOT, Municipalities, Owners of dams and culverts
|  | Identify and protect habitat areas throughout the basin that may have higher resilience to climate change, particularly warming | MBS1.2 | FWAT | USFWS, MEDMR
|  | Develop outreach material to articulate the impacts of climate change on aquatic ecosystems and the mechanisms to combat it | MBS1.3 | Outreach | NMFS, Sea Grant, USFWS
|  | Evaluate and implement Best Management Practices for agriculture and forest lands that may help offset the effects of warming | MBS1.4 | FWAT | USDA-NRCS, Maine Forest Service
Dams and culverts are ubiquitous throughout the Merrymeeting Bay SHRU. Dams and culverts block or impede access to habitats used for spawning and rearing Atlantic salmon; degrade habitat features for native riverine species; alter the biodiversity that native species have adapted to; and block or impair access to lakes and ponds used by many diadromous fish species, particularly alewives that use these areas for feeding, spawning, rearing | MBS2.0 | Seek out opportunities at dams and road crossings throughout the SHRU where access can be improved for diadromous fish, including river herring and Atlantic salmon | MBS2.1 | CAT | NMFS, USFWS, MDMR, PIN, NGO’s
|  | Conduct outreach to educate the public about diadromous fish and their contribution to freshwater ecosystems, and how dams affect them | MBS2.2 | Outreach | NMFS, USFWS, MDMR, NGO’s, owners of barriers
|  | Conduct outreach on the tradeoffs that dams provide as a source of green energy vs. their impacts to fisheries. | MBS2.3 | Outreach | NMFS, Sea Grant, NGO’s
|  | Conduct outreach on dam and culvert removal projects to educate the public on the value of these efforts | MBS2.4 | Outreach | USFWS, NMFS, Sea Grant, NGO’s
|  | Remove all fish passage impediments (dams and culverts) to allow salmon to find and use spawning areas on timescales that they deem necessary. | MBS2.5 | CAT | NMFS, USFWS, UMaine, Sea Grant, NGO’s
|  | Evaluate, through consultation, dam or culvert modification or installation project to assure that projects provide for upstream and downstream passage of all life stages of Atlantic salmon sufficient to sustain recovery. | MBS2.6 | CAT | MEDMR, NMFS, USFWS, NGO's
|  | Assure that consultations on road crossing projects throughout the Merrymeeting Bay SHRU result in cumulative gains in habitat that support survival and recovery | MBS2.7 | CAT | NOAA, USFWS
The stocking and introductions of non-native species, particularly small mouth bass,can compete with and prey on Atlantic salmon in the Merrymeeting Bay SHRU. Headponds associated with dams have degraded habitat features well suited for Atlantic salmon while created habitats particuarly well suited for small mouth bass, subsequently increase predation preasure on juvenile salmon. | MBS3.0 | Assess the impact of non-native species on juvenile salmon, including emigrating smolts and sites where predation occurs most frequently. | MBS3.1 | FWAT | MEDMR, MEDIF&W
|  | Implement fish management activities and regulations that minimizes the spread of invasive species without compromising the recovery of Atlantic salmon and the co-evolved suite of diadromous fish | MBS3.2 | FWAT | MEDMR, MEDIF&W
|  | Conduct outreach on the impacts of invasive species | MBS3.3 | Outreach | MEDMR, MEDIF&W
|  | Implement fish management activities and regulations that help minimize the effects of predation and competition by introduced species | MBS3.4 | FWAT | MEDMR, MEDIF&W
|  | Implement activities that encourage healthy populations of native fish communities and discourage introduced species | MBS3.5 | FWAT | MEDMR, MEDIF&W
The Sheepscot River stock represents the last remaining locally adapted stock in the Merryeeting Bay SHRU compromising the overall fitness of the Gulf of Maine DPS. In addition, except for the Sheepscot, there are no dedicated stocks at Craig Brook or Green Lake Hatcheries set aside for a stocking program within the Merrymeeting Bay SHRU | MBS4.0 | Develop production capacity and an independant donor broodstock program to support the Merrymeeting Bay SHRU that: 1) Preserves and promote the genetic diversity of existing stocks, 2) Prevents the further loss of family groups, 3) allow for marine and freshwater selection to maximize fitness, 4) account for habitat variability and climate change scenarios, and 5) promotes the development of locally adapted stocks | MBS4.1 | GDAT, CHAT | MEDMR, USFWS
Pollution attributed to landuse and development practices in the Merrmeeting Bay SHRU can harm Atlantic salmon and degrade the productive capacity of freshwater and estuary habitats. Types of pollution from landuse and development practices include: Non-point sources of pollution including nutrient runoff and pesticide contamination of surface waters from forestry, agriculture and residential/commercial land use practices; Increased erosion and radiational warming from clearing lands as a result of forest harvesting, agricultural and residential development; chemical and organic pollutants from storm water runoff, combined sewer over flows, and waste water discharge | MBS5.0 | Implement best management practices in forestry and agricultural practices that minimizes soil erosion, nutrient runoff, and pesticide contamination of surface and ground waters | MBS5.1 | FWAT | EPA, USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify and implement landuse best management practices that minimizes radiational warming that can elevate surface water temperatures | MBS5.2 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Implement best management practices that ensures that storm water runoff, combined sewer overflows and waste water discharges do not harm Atlantic salmon and their habitats | MBS5.3 | FWAT | EPA, USFWS, NOAA, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Evaluate whether existing state and federal water quality standards are sufficient to allow for survival and recovery. | MBS5.4 | FWAT | EPA, MEDEP
|  | Evaluate of effects of legacy contaminants in the Merrymeeting Bay SHRU and the extent that it could effect Atlantic slmon survival and recovery | MBS5.5 | FWAT | EPA, MEDEP
|  | Evaluate the affects of water use on minimum flows in the Merrymeeting Bay SHRU | MBS5.6 | FWAT | USGS, MEDEP
The agencies have limited resources to assess all areas that could be occupied by salmon, and therefor many sites with good habitat are not routinely assessed. It is important for the agencies to know if and when rivers and streams are being used by salmon and if salmon are being held up below barriers to migration (dams and culverts). | MBS6.0 | Monitor rivers and streams that are not frequently monitored by the agencies to look for evidence of salmon occupation. | MBS6.1 | FWAT | NGO's
|  | Monitor areas below dams and culverts to look for evidence of salmon occupation. | MBS6.2 | CAT | NGO's
Historic and current landuse have degrade the complexity and productivity of freshwater habitats that support Atlantic salmon in the Downeast SHRU. Types of current and historic land use practices include: historic log drives straightened channels and removed wood and boulders in some areas altering stream flow and habitat complexity; past and current agriculture and forestry practices, and residential development practices have reduced the density and age of trees in the riparian area that provides for shade, cover, bank stability and complexity, and nutrient inputs. | MBS7.0 | Develop and implement a plan that ensures land use practices protect riparian zones in a manner that maximizes riparian zone function | MBS7.1 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify and implement landuse best management practices that ensures protections of Atlantic salmon and their habitats. | MBS7.2 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify, quantify and map river reaches where channel complexity is believe to be most impaired from historic log drive practices. | MBS7.3 | FWAT | MEDMR
|  | Develop a written strategy to restore identified degraded stream reaches that includes productivity goals, metrics to gauge success, and public education | MBS7.4 | FWAT | MEDMR

## MMB Site Specific Threats
MERRYMEETING BAY SHRU SITE SPECIFIC THREATS AND RECOVERY ACTIONS
SITE SPECIFIC THREATS | SUB-BASIN | WATERSHED | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES | DATE LISTED | STATUS/DATE COMPLETED | RECOVERY ACTION IN THE RECOVERY PLAN THAT THE ACTIVITY ADDRESSES
The Sheepscot River stock is especially important to protect because it represents the southernmost locally adapted stock in the U.S. | Sheepscot River | Sheepscot River | M1.0 | Establish a larger sheepscot river broodstock to conserve genetic diversity and then increase distribution through stocking of nearby vacant habitats in the Merrymeeting Bay SHRU, such as the Kennebec and St. George. | M1.1 | GDAT | MEDMR, USFWS | 2015
|  |  |  | Evaluate Sheepscot Broodstock as a doner stock compared to Penobscot donor stock in MMB SHRU vacant habitat through a common garden evaluation | M1.2 | GDAT | MEDMR, USFWS | 2015
Coopers Mills Dam and Head Tide Dam are partial and sometimes complete passage barriers to salmon and other diadromous fish depending on flows | Sheepscot River | Sheepscot River | M2.0 | Remove dam or improve passage at Head Tide Dam in Alna to allow unimpeded passage of diadromous fish, including Atlantic salmon. | M2.1 | CAT | NGO’s, Dam Owners, MEDMR, NOAA | 2015 | Negotiations are underway. 2/2016
|  |  |  | Remove dam or improve passage at Coopers Mills Dam to allow unimpeded passage of diadromous fish, including Atlantic salmon | M2.2 | CAT | NGO’s, Dam Owners, MEDMR, NOAA | 2015 | The town council and citizens committee has adopted ASF proposal to remove the dam. Still needs a town vote. 2/2016
The Sheepscot Lake outlet dam is managed to exclude river herring which subsequently blocks Atlantic salmon passage. River herring are excluded because of concerns that juveniles may clog the Palermo Hatchery intake pipe and also concerns of disease. | Sheepscot River | Sheepscot River | M3.0 | Identify solutions to address the concerns at the Palermo Fish Hatchery | M3.1 | FWAT | MEIF&W, MEDMR, NGO’s, NOAA | 2015
|  |  |  | Implement solutions to address the concerns at the Palermo Fish Hatchery | M3.2 | FWAT | MEIF&W, MEDMR, NGO’s, NOAA | 2015
|  |  |  | Remove dam or improve passage at the Sheepscot Lake outlet to allow for passage of Atlantic salmon and river herring | M3.3 | CAT | MEIF&W, MEDMR, NGO’s, NOAA | 2015
Branch Pond Outlet Dam blocks passage of river herring that are currently stocked in the pond by Maine’s DMR. | Sheepscot River | West Branch Sheepscot River | M4.0 | Remove the dam or install fish passage at the Branch Pond outlet dam to allow for unimpeded passage of river herring | M4.1 | CAT | Dam Owners, MEDMR, NGO’s, NOAA | 2015
Remnant dams in the West Branch Sheepscot affect the quality and accessibility of spawning and rearing habitats | Sheepscot River | West Branch Sheepscot River | M5.0 | Identify and remove remove remnant dams in the Sheepscot River watershed | M5.1 | CAT | Dam Owners, MEDMR, NGO’s, NOAA | 2015
The Sheepscot River watershed has suitable habitats for Atlantic salmon spawning and rearing that currently supports one of eight locally adapted stocks of Atlantic salmon. Landuse practices, development and road crossings can affect the quality and availability of these habitats | Sheepscot River | Sheepscot River | M6.0 | The Sheepscot River is a focus area for proactive efforts to identify and address anthropogenic barriers including dams and road crossings that block or impair access to migratory fish, including Atlantic salmon | M6.1 | CAT | Dam Owners, MDOT, Municipalities, NGO's | 2015
|  |  |  | The Sheepscot River is a focus area for proactive efforts to identify and address landuse and development practices that degrade or impair habitat quality and quantity for migratory fish, including Atlantic salmon | M6.2 | FWAT | Landowners, NRCS, Municipalities, NGO's | 2015
The St. George River, particularly within and above Jam Black Brook has suitable habitats for Atlantic salmon spawning and rearing comparable to that of the Sheepscot River. Land use practices, development and road crossings can affect the quality and availability of these habitats | St. George River and Medomak Rivers | St. George River | M6.0 | The St. George River is a focus area for proactive efforts to identify and address anthropogenic barriers including dams and road crossings that block or impair access to migratory fish, including Atlantic salmon | M6.1 | CAT | Dam owners, Municipalities, MDOT, NGO's | 2015
|  |  |  | The St. George River is a focus area for proactive efforts to identify and address landuse and development practices that degrade or impair habitat quality and quantity for migratory fish, including Atlantic salmon | M6.2 | FWAT | Landowners, NRCS, Municipalities, NGO's | 2015
The St. George River watershed provides considerable opportunities for river herring that are ecologically important to the continued survival of Atlantic salmon, as well as some opportunities for Atlantic salmon spawning and rearing. | St. George River and Medomak Rivers | St. George River | M7.0 | Continue to work with the towns in the St. George watershed to ensure passage of river herring and seek out new opportunities to optimize fish productivity. | M7.1 | CAT | MEDMR, NMFS, USFWS, MDOT, NGO’s | 2015
The Medomak watershed provides considerable opportunities for river herring, particularly in Washington Pond. River Herring are ecologically important to the continued survival of Atlantic salmon. The Medomak also has some opportunities for Atlantic salmon spawning and rearing. | St. George River and Medomak Rivers | Medomak | M8.0 | Continue to work with the towns in the Medomak watershed to ensure passage of river herring and Atlantic salmon and seek out new opportunities to optimize fish productivity. | M8.1 | CAT | MEDMR, NMFS, USFWS, MDOT, NGO’s | 2015
On the mainstem of the Androscoggin River, the Brunswick, Pejepscot and Worumbo Dams and their operations can: 1) Block and impede access of Atlantic salmon and co-evolved diadromous species; 2) Directly and indirectly kill or harm Atlantic salmon; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbate the effects of climate change | Androscoggin River and its tributaries | Mainstem Androscoggin | M9.0 | Develop a final species protection plan and adjust operations at these dams such that they meet or exceed any upstream and downstream fish passage efficiency standards required to allow for survival and recovery of Atlantic salmon. | M9.1 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan. | M9.2 | CAT | owners and operators of the dams, FERC, NMFS | 2015
On the mainstem of the Androscoggin River the Lewiston Falls hydro project is at the upper extent of critical habitat. Despite this, the dam and its operations’ can harm Atlantic salmon by 1) blocking and/or impeding Atlantic salmons instinct to migrate; 2) blocking or impeding salmon’s co-evolved diadromous species that may buffer salmon from predation and provide essential nutrients that juvenile salmon depend on; 2) directly and indirectly kill or harm Atlantic salmon that attempt to pass or that are delayed during their migration; 3) Alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbating the effects of climate change creating environmental conditions less suitable for salmon survival. | Androscoggin River and its tributaries | Mainstem Androscoggin | M10.0 | Develop a final species protection plan and adjust operations at these dams such that they meet or exceed any upstream and downstream fish passage efficiency standards required to provide for survival and recovery of Atlantic salmon. | M10.1 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan. | M10.2 | CAT | owners and operators of the dams, FERC, NMFS | 2015
Given the current configuration of dams in the Androscoggin, the Little River currently provides the best opportunities for Atlantic salmon spawning and rearing. This should be preserved for any adult Atlantic salmon returning to the Androscoggin River. | Androscoggin River and its tributaries | Little River | M11.0 | the Little River is a focus area for identifying and address anthropogenic barriers that block or impair access to migratory fish, including Atlantic salmon because of the limited opportunities with the Androscoggin River for Atlantic salmon spawning and rearing, | M11.1 | CAT | Soil and water conservation district, MDOT, municipalities, MEDMR | 2015
|  |  |  | The Little River is a focus area for ensuring that land use and development projects protect habitat and water quality features that salmon most often select for spawning and juvenile rearing because of the limited opportunities within the Androscoggin River for Atlantic salmon spawning and rearing. | M11.2 | FWAT | Soil and water conservation district, MDOT, MDEP, municipalities, MEDMR | 2015
The Sabbatus River provides considerable potential for river herring restoration. River herring are an important predator buffer and nutrient vector that support Atlantic salmon. Maine DMR has identified the Sabbatus as one of their top priorities for restoration. Currently five dams block or impair access of river herring into Sabbatus Pond. | Androscoggin River and its tributaries | Sabbatus River | M12.0 | Work with dam owners along the Sabbatus River to explore dam removal or fish passage improvements that maximize the production potential of river herring in Sabbatus Pond, and allow for the survival and recovery of Atlantic salmon | M12.1 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015 | Owner of lower dam is not budging on dam removal. This has put a hold on work on the other dams in the watershed. 2/2016
|  |  |  | Ensure landuse and development along the Sabbatus River and around Sabbatus Pond is protective of freshwater habitats and water quality that river herring require to be successful. | M12.2 | FWAT | Municipalities, Landowners, MDEP, NGO’s, MEDMR, NOAA | 2015
The Little Androscoggin River is not part of the designated critical habitat. Despite this, Atlantic salmon can enter the mouth of the Little Androscoggin up to Lower Barker Dam. Lower Barker dam and its operations’ can harm Atlantic salmon by 1) blocking and/or impeding Atlantic salmons instinct to migrate; 2) blocking or impeding salmon’s co-evolved diadromous species that may buffer salmon from predation and provide essential nutrients that juvenile salmon depend on; 2) directly and indirectly kill or harm Atlantic salmon that attempt to pass or that are delayed during their migration; 3) alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbating the effects of climate change creating environmental conditions less suitable for salmon survival. | Androscoggin River and its tributaries | Little Androscoggin River | M13.0 | Develop a final species protection plan for the Lower Barker Dam and adjust operations at these dams such that they meet or exceed any upstream and downstream fish passage efficiency standards allow for the survival and recovery of Atlantic salmon. | M13.1 | CAT | owners and operators of the dams, FERC, NMFS | 2015
|  |  |  | Evaluate and modify operations of the Lower Barker Dam as needed until operations meet or exceed the specified standards. Standards must be met within ten years of the completion of any final species protection plan. | M13.2 | CAT | owners and operators of the dams, FERC, NMFS | 2015
The Cobbosseecontee provides considerable potential for river herring restoration. River herring are an important predator buffer and nutrient vector that support Atlantic salmon. | Lower Kennebec River below Lockwood, including Cobbosseecontee Stream, Togus Stream, Bond Brook | Cobbosseecontee Stream | M14.0 | Work with dam owners along the Cobbosseecontee to explore dam removal or fish passage improvements that maximize the production potential of river herring in Cobbosseecontee lake. | M14.1 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
Togus Stream – Togus Stream has good habitat for Atlantic salmon and Togus Pond is currently stocked with alewives. Currently there is a dam at the outlet of Togus Pond that blocks alewife passage. | Lower Kennebec River below Lockwood, including Cobbosseecontee Stream, Togus Stream, Bond Brook | Togus Stream | M15.0 | Work with dam owner of the Togus Pond dam to explore dam removal or fish passage improvements that maximize the production potential of river herring in Togus Pond. | M15.1 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
Bond Brook has been known to have productive Atlantic salmon habitat. Although it is heavily impaired by residential development, Bond Brook is one of a few number of tributaries that salmon have access to below Lockwood Dam for spawning and juvenile rearing | Lower Kennebec River below Lockwood, including Cobbosseecontee Stream, Togus Stream, Bond Brook | Bond Brook | M16.0 | Bond Brook is a focus area for identifying and address anthropogenic barriers that block or impair access to migratory fish, including Atlantic salmon because of the limited opportunities with the Kennebec River below the Lockwood Dam for Atlantic salmon spawning and rearing, | M16.1 | CAT | MDOT, City of Augusta, NGO’s, MEDMR, NOAA | 2015
|  |  |  | Bond Brook is a focus area to ensure landuse and development along Bond Brook is protective of freshwater habitats and water quality that river herring and Atlantic salmon require to be successful because of the limited opportunities with the Kennebec River below the Lockwood Dam for Atlantic salmon spawning and rearing. | M16.2 | FWAT | Municipalities, Landowners, MDEP, NGO’s, MEDMR, NOAA | 2015
Though the Sabasticook Watershed is not part of the designated Critical Habitat for Atlantic salmon, the Sabasticook provides considerable opportunities for river herring production as well as some opportunities for Atlantic salmon spawning and rearing. Several dams within the basin limit the productive capacity of river herring and Atlantic salmon within the system because of impaired or obstructed passage. | Sabasticook River | Sabasticook River | M17.0 | Work with owners of the five dams on China Lakes’ outlet stream to explore opportunities for dam removal or improved fish passage in order to maximize the production of river herring | M17.1 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
|  |  |  | Address flow issues at the Burnham dam to improve passage of river herring and minimize the potential for harm to Atlantic salmon | M17.2 | CAT | Dam Owners, MEDMR, NGO’s | 2015
|  |  |  | Work with the owners of the Great Moose Dam to explore opportunities for dam removal or improved fish passage to maximize production of river herring | M17.3 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
|  |  |  | Work with the owners of the Waverly Dam to explore opportunities for dam removal or improved fish passage to maximize production of river herring | M17.4 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
|  |  |  | Work with the owners of the Pioneer Dam to explore opportunities for dam removal or improved fish passage to maximize production of river herring | M17.5 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
|  |  |  | Assess the fish passage efficiency at Benton Falls to assure that the operations allow for the survival and reocvery of Atlantic salmon, and minimize the potential for harm | M17.6 | CAT | Dam Owners, NGO’s, MEDMR, NOAA | 2015
The Lockwood hydro project is currently operating under interim species protection plan. This dam and its operations can block, impair or delay passage of Atlantic salmon adults and smolts, may cause direct or indirect mortality and alter the physical and biological features that salmon depend on for their survival. | Kennebec River between Lockwood Dam and the Carrabasset River | Mainstem Kennebec River | M18.0 | Develop performance standards for Lockwood and incorporate them into a final species protection plan. Final SPP’s will be in place for hydro Kennebec by 2017, and the other projects by 2020. | M18.1 | CAT | NOAA | 2015
|  |  |  | Conduct downstream survival studies to assess effects of the Lockwood Dam on smolt survival, and modify opperations to improve survival necessary to meet or exceed performance standards. | M18.2 | FWAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
|  |  |  | Construct effective upstream fish passage at Lockwood by 2019. | M18.3 | CAT | Dam Owner | 2015
|  |  |  | Test upstream survival and fish passage efficiency at the Lockwood facility by 2019 to assure that the effects of the dam and its operations’ meet or exceed the performance standards. | M18.4 | CAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
|  |  |  | Conduct routine inspections of Lockwood tailrace to assure adult salmon are not being held up. | M18.5 | CAT | Dam Owner, NOAA, MEDMR | 2015
The Hydro-Kennebec project is currently all operating under interim species protection plans. This dam and its current operations can block, impair or delay passage of Atlantic salmon adults and smolts, may cause direct or indirect mortality and alter the physical and biological features that salmon depend on for their survival. | Kennebec River between Lockwood Dam and the Sandy River | Mainstem Kennebec River | M19.0 | Develop performance standards for the Hydro-Kennebec dam and incorporate them into a final species protection plan. Final SPP's will be in place by 2017. | M19.1 | CAT | NOAA | 2015
|  |  |  | Conduct downstream survival studies to assess effects of this project on smolt survival, and modify opperations to improve survival necessary to meet or exceed performance standards. | M19.2 | FWAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
|  |  |  | Construct effective upstream fish passage at Hydro-Kennebec by 2019. | M19.3 | CAT | Dam Owner | 2015
|  |  |  | Test upstream survival and fish passage efficiency at the Hydro-Kennebec facility to assure that the effects of the dam and its operations’ meet or exceed the performance standards. | M19.4 | CAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
The Shawmut hydro project is currently operating under interim species protection plans. This dam and its current operations can block, impair or delay passage of Atlantic salmon adults and smolts, may cause direct or indirect mortality and alter the physical and biological features that salmon depend on for their survival. | Kennebec River between Lockwood Dam and the Sandy River | Mainstem Kennebec River | M20.0 | Develop performance standards for the Shawmut dam and incorporate them into a final species protection plan. Final SPP’s will be in place by 2020. | M20.1 | CAT | NOAA | 2015
|  |  |  | Conduct downstream survival studies to assess effects of these projects on smolt survival, and modify opperations to improve survival necessary to meet or exceed performance standards. | M20.2 | FWAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
|  |  |  | Construct effective upstream fishpassage at Shawmut by 2019. | M20.3 | CAT | Dam Owner | 2015
|  |  |  | Test upstream survival and fish passage efficiency at Shawmut to assure that the effects of the dam and its operations’ meet or exceed the performance standards. | M20.4 | CAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
The Weston hydro project is currently operating under interim species protection plan. This dam and its current operations can block, impair or delay passage of Atlantic salmon adults and smolts, may cause direct or indirect mortality and alter the physical and biological features that salmon depend on for their survival. | Kennebec River between Lockwood Dam and the Sandy River | Mainstem Kennebec River | M21.0 | Develop performance standards for Weston and incorporate them into a final species protection plan. Final SPP’s will be in place for by 2020. | M21.1 | CAT | NOAA | 2015
|  |  |  | Conduct downstream survival studies to assess effects of these projects on smolt survival, and modify opperations to improve survival necessary to meet or exceed performance standards. | M21.2 | FWAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
|  |  |  | Construct effective upstream fishpassage at Weston by 2019. | M21.3 | CAT | Dam Owner | 2015
|  |  |  | Test upstream survival and fish passage efficiency at Shawmut to assure that the effects of the dam and its operations’ meet or exceed the performance standards. | M21.4 | CAT | Dam owner, FERC, NOAA, MEDMR, USFWS | 2015
The Sandy River has very abundant, high quality habitats. A small privately owned, FERC exempt dam on Lemon Stream, a dam being considered for redevelopment at the outlet of Wilson Pond Outlet Dam, and the Temple Stream Dam block or impair high quality habitats that are or could support Atlantic salmon spawning and rearing. | Sandy River and its Tributaries | Lemon Stream, Wilson Pond, and Temple Stream | M22.0 | Work with the owner of the dam on Lemon Stream to explore opportunities for either dam removal or fish passage that allows for the survival and recovery of Atlantic salmon. | M22.1 | CAT | Dam owner, MEDMR, USFWS, NOAA, NGO’s | 2015
|  |  |  | Work with the owner of the Wilson Pond outlet dam to explore opportunities for either dam removal or fish passage that allows for the survival and recovery of Atlantic salmon. | M22.2 | CAT | Dam owner, MEDMR, USFWS, NOAA, NGO’s | 2015
|  |  |  | Work with the owner of the Temple Stream dam to explore opportunities for either dam removal or fish passage that allows for the survival and recovery of Atlantic salmon. | M22.3 | CAT | Dam owner, MEDMR, USFWS, NOAA, NGO’s | 2015
The entire Kennebec and Androscoggin basin, but particularly the Sandy River relies on the availability of out of basin eggs and fry to fulfill any stocking or recolonization goals. Low adult returns in the Penobscot and budget constraints can threaten the availability of eggs for these programs. | Sandy River and its Tributaries | Sandy River and Its Tributaries | M23.0 | The Sandy River is a priority area for receiving a donor stock from an out of basin source for population rebuilding in the MMB SHRU. | M23.1 | CHAT, GDAT | Dam Owners, USFWS, MEDMR | 2015
The Carrabasset River has very abundant, high quality Atlantic salmon spawning and nursery habitats. Both the Anson and Abenaki Dams block access to the Carrabasset River. Therefor these projects may harm salmon if salmon were to approach them and passage was not allowed. Harm of Atlantic salmon at these dams can occur by 1) blocking passage; 2) directly and indirectly kill or harm Atlantic salmon that are unable to pass; 3) alter flow and sediment transport that creates freshwater habitats and stimulates migratory behaviors that salmon are adapted to; and 4) Exacerbating the effects of climate change creating environmental conditions less suitable for salmon survival. | Kennebec River above Sandy River including the Carrabasset River | Kennebec River above Sandy River including the Carrabasset River | M24.0 | Develop performance standards for the Abenaki dam and incorporate them into a final species protection plan to assure its operations’ allow for Atlantic salmon survival and recovery. | M24.1 | CAT | NOAA | 2015
|  |  |  | Construct upstream fish passage at Abenaki by 2021. | M24.2 | CAT | Dam Owner | 2015
|  |  |  | Develop performance standards for the Anson Dam and incorporate them into a final species protection plan to assure its operations’ allow for Atlantic salmon survival and recovery. | M24.3 | CAT | NOAA | 2015
|  |  |  | Construct upstream fish passage at Anson by 2021. | M24.4 | CAT | Dam Owner | 2015
|  |  |  | Conduct habitat surveys in the Carrabasset River to identify the quantity and quality of habitat features, and opportunities for restoration | M24.5 | FWAT | MEDMR | 2015

## DE SHRU Threats
DOWNEAST SHRU OVERARCHING THREATS AND RECOVERY ACTIONS
OVERARCHING THREATS WITHIN THE DOWNEAST SHRU | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES
Climate change has, and will likely continue to change the spatial landscape of habitats most suitable for Atlantic salmon. Throughout the basin there are areas that may be more vulnerable to climate change and may become less suitable for Atlantic salmon, while other areas may be more resilient and warrant greater protection. | DES1.0 | Remove all fish passage impediments (dams, culverts, remnant dams) to allow salmon to find and use areas of cold water refuge on timescales that they deem necessary. | DES1.0 | CAT | NGO's, DOT, Municipalities, Owners of dams and culverts
|  | Identify and protect habitat areas throughout the basin that may have higher resilience to climate change, particularly warming | DES1.2 | FWAT | USFWS, MEDMR
|  | Develop outreach material to articulate the impacts of climate change on aquatic ecosystems and the mechanisms to combat it | DES1.3 | Outreach | NMFS, Sea Grant, USFWS
|  | Evaluate and implement Best Management Practices for agriculture and forest lands that may help offset the effects of warming | DES1.4 | FWAT | USDA-NRCS, Maine Forest Service
Dams and culverts are ubiquitous throughout the Downeast SHRU. Dams and culverts block or impede access to habitats used for spawning and rearing Atlantic salmon; degrade habitat features for native riverine species; alter the biodiversity that native species have adapted to; and block or impair access to lakes and ponds used by many diadromous fish species, particularly alewives that use these areas for feeding, spawning, rearing | DES2.0 | Seek out opportunities at dams and road crossings throughout the SHRU where access can be improved for diadromous fish, including river herring and Atlantic salmon | DES2.1 | CAT | NMFS, USFWS, MDMR, NGO’s, owners of barriers
|  | Conduct outreach to educate the public about diadromous fish and their contribution to freshwater ecosystems, and how dams affect them | DES2.2 | Outreach | NMFS, Sea Grant, NGO’s
|  | Conduct outreach on the tradeoffs that dams provide as a source of green energy vs. their impacts to fisheries. | DES2.3 | Outreach | USFWS, NMFS, Sea Grant, NGO’s
|  | Conduct outreach on dam and culvert removal projects to educate the public on the value of these efforts | DES2.4 | Outreach | NMFS, USFWS, UMaine, Sea Grant, NGO’s
|  | Remove all fish passage impediments (dams and culverts) to allow salmon to find and use spawning areas on timescales that they deem necessary. | DES2.6 | CAT | MEDMR, NOAA, USFWS, NGO's
|  | Evaluate, through consultation, dam or culvert modification or installation project to assure that projects provide for upstream and downstream passage of all life stages of Atlantic salmon sufficient to sustain recovery. | DES2.7 | CAT | NMFS, USFWS
|  | Assure that consultations on road crossing projects throughout the DowneastSHRU result in cumulative gains in habitat that support survival and recovery | DES2.8 | CAT | NMFS, USFWS
Stocking and introductions of non-native species, particularly small mouth bass,can compete with and prey on Atlantic salmon in the Downeast SHRU. Headponds associated with dams have degraded habitat features well suited for Atlantic salmon while created habitats particuarly well suited for small mouth bass, subsequently increase predation preasure on juvenile salmon. | DES3.0 | Assess the impact of non-native species on juvenile salmon, including emigrating smolts and sites where predation occurs most frequently. | DES3.1 | FWAT | MEDMR, MEDIF&W
|  | Implement fish management activities and regulations that minimizes the spread of invasive species without compromising the recovery of Atlantic salmon and the co-evolved suite of diadromous fish | DES3.2 | FWAT | MEDMR, MEDIF&W
|  | Conduct outreach on the impacts of invasive species | DES3.3 | Outreach | MEDMR, MEDIF&W
|  | Implement fish management activities and regulations that help minimize the effects of predation and competition by introduced species | DES3.4 | FWAT | MEDMR, MEDIF&W
|  | Implement activities that encourage healthy populations of native fish communities and discourage introduced species | DES3.5 | FWAT | MEDMR, MEDIF&W
Pollution attributed to landuse and development practices in the Downeast Bay SHRU can harm Atlantic salmon and degrade the productive capacity of freshwater and estuary habitats. Types of pollution from landuse and development practices include: Non-point sources of pollution including nutrient runoff and pesticide contamination of surface waters from forestry, agriculture and residential/commercial land use practices; Increased erosion and radiational warming from clearing lands as a result of forest harvesting, agricultural and residential development; chemical and organic pollutants from storm water runoff, combined sewer over flows, and waste water discharge | DES4.0 | Implement best management practices in forestry and agricultural practices that minimizes soil erosion, nutrient runoff, and pesticide contamination of surface and ground waters | DES4.1 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify and implement landuse best management practices that minimizes radiational warming that can elevate surface water temperatures | DES4.2 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Implement best management practices that ensures that storm water runoff, combined sewer overflows and waste water discharges do not harm Atlantic salmon and their habitats | DES4.3 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Evaluate whether existing state and federal water quality standards are sufficient to allow for survival and recovery. | DES4.4 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Evaluate of effects of legacy contaminants in the Downeast SHRU and the extent that it could effect Atlantic slmon survival and recovery | DES4.5 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Evaluate the affects of water use on minimum flows in the Downeast SHRU | DES4.6 | FWAT | USFWS, NOAA, USDA-NRCS, Forest Products Industry, Agriculture Industries
Historic and current landuse have degrade the complexity and productivity of freshwater habitats that support Atlantic salmon in the Downeast SHRU. Types of current and historic land use practices include: historic log drives straightened channels and removed wood and boulders in some areas altering stream flow and habitat complexity; past and current agriculture and forestry practices, and residential development practices have reduced the density and age of trees in the riparian area that provides for shade, cover, bank stability and complexity, and nutrient inputs. | DES5.0 | Develop and implement a plan that ensures land use practices protect riparian zones in a manner that maximizes riparian zone function | DES5.1 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify and implement landuse best management practices that ensures protections of Atlantic salmon and their habitats. | DES5.2 | FWAT | USFWS, USDA-NRCS, Forest Products Industry, Agriculture Industries
|  | Identify, quantify and map river reaches where channel complexity is believe to be most impaired from historic log drive practices. | DES5.3 | FWAT | MEDMR
|  | Develop a written strategy to restore identified degraded stream reaches that includes productivity goals, metrics to gauge success, and public education | DES5.4 | FWAT | MEDMR
The small population size and small number of remaining family groups within the Downeast Coastal SHRU compromises the overall fitness of the Gulf of Maine DPS. Reliance on a parr broodstock program may also compromise marine fitness as fewer fish that have undergone marine selection are contributing to the population. | DES6.0 | Develop and implement a broodstock and stocking strategy that: 1) Preserves and promote the genetic diversity of existing stocks, 2) Prevents the further loss of family groups, 3) allow for marine and freshwater selection to maximize fitness, and 4) account for habitat variability and climate change scenarios | DES6.1 | GDAT, CHAT | MEDMR, USFWS
The agencies have limited resources to assess all areas that could be occupied by salmon, and therefor many sites with good habitat are not routinely assessed. It is important for the agencies to know if and when rivers and streams are being used by salmon and if salmon are being held up below barriers to migration (dams and culverts). | DES7.0 | Monitor rivers and streams that are not frequently monitored by the agencies to look for evidence of salmon occupation. | DES7.1 | FWAT | NGO's
|  | Monitor areas below dams and culverts to look for evidence of salmon occupation. | DES7.2 | CAT | NGO's

## DE Site Specific Threats
DOWNEAST SHRU SITE-SPECIFIC THREATS AND RECOVERY ACTIONS
SITE SPECIFIC THREATS | SUB-BASIN | WATERSHED | THREAT NUMBER | RECOVERY ACTIVITY | ACTIVITY NUMBER | REPORTING ACTION TEAM | IMPLEMENTING ENTITIES | DATE LISTED | STATUS/DATE COMPLETED | RECOVERY ACTION IN THE RECOVERY PLAN THAT THE ACTIVITY ADDRESSES
The Dennys River stock has much lower return rates than other rivers in the DPS that may be a function of natural or manmade conditions in the freshwater and/or estuary of the Dennys, or me be a function of a loss of genetic fitness within the Dennys River stock. | Dennys River | Dennys River | D1.0 | Design and implement study to identify the cause for low return rates for the Dennys River Stock | D1.1 | CHAT | NMFS, MEDMR | 2015
The Greatworks Dam, Meddybemps Dam, and Cathance Lake Dam impair habitat quality and impede access of alewives and salmon to habitat resources | Dennys River | Dennys and Cathance | D2.0 | Conduct feasibility study of Greatworks Dam in Cathance to improve habitat quality and habitat access for salmon and river herring | D2.1 | CAT | NGO's, NMFS, MEDMR, MEDIF&W | 2015
|  |  |  | Review IFIM for the operations of Meddybemps Dam to assure that it accounts for climate change | D2.2 | CAT | NMFS | 2015
|  |  |  | Maintain and improve passage at Meddybemps and Cathance Dams to maximize passage efficiency of salmon and alewives | D2.3 | CAT | MEDMR, MEDOT | 2015
Curry and Preston Brooks are important sources of cold water to the Dennys River. Road crossings can impair access and water quality within these tributaries. | Dennys River | Curry and Preston Brooks | D3.0 | Work with landowners along Curry Brook to identify ways to minimize the impacts of road crossings on water quality and connectivity | D3.1 | CAT | NGO's, USFWS | 2015
|  |  |  | Work with landowners along Preston Brook to identify ways to minimize the impacts of road crossings on water quality and connectivity | D3.2 | CAT | NGO's, USFWS | 2015
Culverts and remnant dams in the tributaries of the East Machias, particularly Beaver Dam Stream, Chase Mill Stream and Northern Stream, reduce water quality and access to the most abundant and most suitable nursery habitat in the watershed, likely impeding survival of the East Machias stock. | East Machias River | Beaver Dam Stream, Chase Mill Stream, Northern Stream | D4.0 | Identify and remove passage barriers in Beaver Dam Stream. | D4.1 | CAT | NGO's | 2015
|  |  |  | Identify and remove passage barriers in Chase Mill Stream. | D4.2 | CAT | NGO's | 2015
|  |  |  | Identify and remove passage barriers in Northern Streams. | D4.3 | CAT | NGO's | 2015
The fishway at Pokey Dam, if not maintained, can impede or block passage to significant alewife spawning and nursery habitats as well as Atlantic salmon resting and nursery habitats | East Machias River | East Machias River | D5.0 | Maintain, and if necessary, improve passage at Pokey Dam to maximize passage of salmon and alewives | D5.1 | CAT | MEDMR, Crawford Lake Association | 2015
The Gardner Lake Fish Hatchery on Chase Mill Stream may still be leaking some fish from the hatchery that may pose a genetic risk to the East Machias locally adapted stock of Atlantic salmon | East Machias River | Chase Mill Stream | D6.0 | Gather genetic samples of parr in Chase Mill stream to look for escapes from the Gardner Lake Hatchery | D6.1 | GDAT | MEDMR | 2015
Storm and waste water discharge from the town of East Machias may impair water quality that could affect Atlantic salmon | East Machias River | East Machias River | D7.0 | Assure storm and waste water discharge does not impair water quality necessary for salmon survival | D7.1 | FWAT | Town of East Machias, USDA, USFWS, NMFS | 2015
The outlet dam at Sabao Lake on the West Branch Machias, Chain Lake dam on Chain Lake Stream, and Wizgig Dam on Old Stream block or impede access to nursery habitats for Atlantic salmon and alewives and affect water quality by reducing stream flow. | Machias River | West Branch Machias, Chain Lake Stream, and Old Stream | D8.0 | Remove or improve passage at Sabao Lake Dam, to allow unimpeded passage of salmon and river herring. | D8.1 | CAT | NGO's, dam owners | 2015
|  |  |  | Remove or improve passage at Chain Lake Dam, to allow unimpeded passage of salmon and river herring | D8.2 | CAT | NGO's, dam owners | 2015
|  |  |  | Remove or improve passage at the Wizgig Dam to allow unimpeded passage of salmon and river herring | D8.3 | CAT | NGO's, dam owners | 2015
On 3rd lake stream in the Machias, wing dams were constructed on side channels during the log drive era in an effort to straighten the channel and prevent log jams. | Machias River | 3rd Lake Stream | D9.0 | Remove wing dams on 3rd lake stream and assess changes to water quality, sediment transport, and habitat use by salmon to determine its value towards salmon recovery. | D9.1 | FWAT | DMR, NGO's, land owners | 2015
On the Middle River, the Machias Dike and Marks Lake Dam block access for migratory fish, particularly alewives | Machias River | Middle River | D10.0 | Restore safe and effective passage for diadromous fish at the Machias Dike and at Marks Lake Dam on the Middle River | D10.1 | CAT | MDOT, NGO's, NMFS | 2015
Access to freshwater habitats and water quality are impaired by culverts, especially in Colonel Brook which has some of the more productive salmon habitats in the Pleasant River | Pleasant River | Colonel Brook | D11.0 | Remove or improve passage at culverts and remnant dams, especially in Colonel Brook to improve passage and water quality | D11.1 | CAT | NGO’s, Landowners | 2015
The fishway at Saco Falls is in need of maintenance which may impair fish passage | Pleasant River | Pleasant River | D12.0 | Make improvements at the Saco Falls fishway to ensure safe and effective passage of salmon and river herring | D12.1 | CAT | MEDMR | 2015
Agricultural practices and irrigation may be affecting water quality, water temperature and water quantity in the Pleasant River. | Pleasant River | Pleasant River | D13.0 | Assess the effectiveness of the WUMP in protecting the Pleasant from the effects of water withdrawal | D13.1 | FWAT | MEDEP, USGS | 2015
The Addison tide gates impairs access to the West Branch Pleasant River and significantly reduces the ecological function of the adjacent salt marsh | Pleasant River | West Branch Pleasant River | D14.0 | Remove the Addison Tide gates to restore diadromous fish access to the West Branch Pleasant River and restore the ecological function of the salt marsh | D14.1 | CAT | MEDOT, NGO’s | 2015
The Stillwater Dam in Cherryfield delays and sometimes blocks passage of Atlantic salmon, shad and river herring. Passage delays increases opportunities for predation by birds. The dam may also affect water quality and its head pond covers a historically important holding pool for adults. | Narraguagus River | Narraguagus River | D15.0 | Conduct a feasibility study/alternatives analysis for the Stillwater Dam | D15.1 | CAT | ACOE, USGS, NOAA,, MEDMR, NGO’s, Town of Cherryfield | 2015
|  |  |  | Implement the best fit alternative at the Stillwater Dam that results from the feasibility study | D15.2 | CAT | ACOE, USGS, NOAA,, MEDMR, NGO’s, Town of Cherryfield | 2015
The Narraguagus River estuary has deposits of wood chips and saw dust from 19th and early 20th century saw mills that, in areas, is several feet deep. These deposits alter benthic habitats and may alter stream flow and morphology that may affect salmon. | Narraguagus River | Narraguagus River estuary | D16.0 | Research the benthic habitats in the Narraguagus estuary and the role that dredging might play in estuary restoration | D16.1 | MEAT | NOAA | 2015
Birds observed in the Narraguagus estuary are known to prey on emigrating smolts. Manmade features, such as bridges, piers and dams can give predators a competitve advantage by creating obstructions that slow fish migrations causing fish to congregate, or creating roosting sites that increase opportunities for birds to spot and feed on prey. | Narraguagus River | Narraguagus River estuary | D17.0 | Identify and remove artifical barriers or features that increase opportunities for predation. | D17.1 | CAT | NGO's, NOAA | 2015
Thermal issues appear to be a problem in the mainstem Narraguagus. This may be a function of clearing of nearby forests for agriculture, irrigation, problems with stream channel morphology, climate change, and remnant dams, dams and culverts that slow down water. | Narraguagus River | Narraguagus River | D18.0 | Remove dams, culverts and remnant dams, especially in the upper Narraguagus, Shorey, and Humpback Brook to improve water quality. | D18.1 | CAT | NGO’s, MEDMR | 2015
|  |  |  | Assess the effectiveness of the WUMP in protecting the Narraguagus from the effects of water withdrawal | D18.2 | FWAT | USFWS, USGS, MEDEP | 2015
|  |  |  | Ensure land managers implement BMP’s that are protective of Atlantic salmon and salmon habitat | D18.3 | FWAT | MEDEP, USFWS, Land Managers | 2015
Portions of the Narraguagus appear to be over wide and void of structure including boulders and large wood. Despite abundant glacial erratic’s in the riparian area, there are long stretches of mainstem habitats with very few if any large boulders or large wood features that would help support habitat features that juvenile salmon select for. | Narraguagus River | Narraguagus River | D19.0 | Design and Implement a large wood/boulder project in the Narraguagus around Rt. 9 and assess its benefits to fish and water quality | D19.1 | FWAT | NGO’s, land managers, MEDMR, USFWS | 2015
The Ellsworth Dam impairs upstream and downstream passage efficiency of adult salmon, smolts, and other diadromous fish, and decreases water quality above the dam. Graham Station does not have an upstream fishway blocking all upstream migratory fish. Current operations block upstream migration of diadromous fish and may delay or block downstream migration of emigrating smolts and other diadromous fish | Union River | Union River | D20.0 | Continue to provide fry to the Union River Salmon Association to support stock rebuilding efforts in the Union River | D20.1 | CHAT | USFWS, MEDMR | 2015
|  |  |  | Ensure hydro operations at the Ellsworth Dam minimizes harm to Atlantic salmon and adverse effects to their Critical Habitat | D20.2 | CAT | NMFS, USFWS, FERC, Hydro-Developers | 2015
|  |  |  | Ensure hydro operations at the Graham Station minimizes harm to Atlantic salmon and adverse effects to their Critical Habitat | D20.3 | CAT | NMFS, USFWS, FERC, Hydro-Developers | 2015
|  |  |  | Develop a stock rebuilding and management plan for the Union River | D20.4 | CHAT, GDAT | MEDMR, USFWS, NMFS | 2015
Limited resources restrict our ability to evaluate habitats within these areas to check for occupancy and ensure protections of those fish and the habitats that they occupy | Boise Bubert, Chandler River, Grand Manan, Lamoine Coastal, Mt. Desert, Roque Bluff, and Tunk Stream | Boise Bubert, Chandler River, Grand Manan, Lamoine Coastal, Mt. Desert, Roque Bluff, and Tunk Stream | D21.0 | Every five years monitor areas that have accessible and suitable habitats where straying might occur to check for occupancy. | D21.1 | FWAT | MEDMR | 2015
|  |  |  | In areas with suitable habitats, implement proactive restoration when opportunities arise (e.g. a dam owner willing to remove his/her dam). | D21.2 | FWAT, CAT | NGO’s, MEDMR, USFWS, MEDOT, NMFS, Landowners, Municipalities | 2015