Summary of Progress Northeast Landscape Conservation Design and Regional Conservation Synthesis for SWAP Updates

In June 2011, at the Northeast Conservation Framework (“Albany 2”) Workshop, priority landscape conservation science needs were assessed and prioritized by northeast conservation partners.  A clear consensus out of that workshop was the need for better communications, science translation and adoption for completed, ongoing and future projects.  Among the top priorities were:

- immediate organization of existing data to make information more available;

- synthesis of existing data to develop/compile landscape designs that will allow partners to map and prioritize focus areas for conservation;

- translation of maps and other tools to make landscape design data useful at various scales and in various formats; and

- assistance to ensure that science and tools are understood and consistently adopted and implemented in support of on-the-ground conservation.

To help address these needs, the North Atlantic LCC hired a Conservation Design Specialist (Steve Fuller) and developed a proposal for a Northeast Landscape Conservation Design to address these priorities.

A brief timeline and summary of progress follows:

February, 2012: Northeast Landscape Conservation Design proposal approved by LCC Steering Committee

March, 2012: LCC and NEAFWA held a joint meeting in Baltimore, MD with FWS, AFWA and state partners to develop full proposals for two RCN projects: Northeast Regional Conservation Synthesis and Components for State Wildlife Action Plan Revisions and Northeast State Wildlife Action Plan (SWAP) Common Lexicon and Web-searchable Framework.  LCC is responsible for synthesis of regional spatial data.

April, 2012: Northeast Directors approved RCN synthesis proposal; Meeting of an initial Northeast Landscape Conservation Design team at NEAFWA Conference.

August, 2012: GIS Analyst (Lori Pelech) hired by the LCC to support this project

September 2012: Workshop on Regional Synthesis project at Northeast Fish and Wildlife Diversity Technical Committee Meeting; Data requests for Regional Species of Greatest Conservation Need to states and NatureServe

December, 2012 : GIS Analyst (Alex Jospe) hired jointly by The Nature Conservancy and LCC  to support project

April, 2012: Regional species data received from states and NatureServe; workshop with states on regional synthesis at NEAFWA Conference.

April-December, 2012: Development of final synthesis document.