NE Synthesis Committee Conference Call

4-23-13 Agenda and Notes

Attendance:

ME-Charlie Todd, Merry Gallagher

DE-Kevin Kalasz

NY Lisa Holst, Dan Rosenblat

VA –Becky Gwynn

Synthesis team: NH- Jeff Tash, S Fuller, kt

Purpose of Call:

- Project Update

- Steering Committee Input on  key questions/decisions for guidance and

- Establish an efficient approach to reviewing the 2 deliverables: Synthesis  and RCN report Content and Format

Goal- Brief Update Call -- Contract requires monthly calls

Update

NEAFWA synthesis committee workshops/meetings

- 10 of 14 states represented

- Great feedback on both projects- database and synthesis

- Coordinated to help both move ahead

KT summarized NEAFWA highlights and updated committee on status.  Synthesis team is incorporating their comments.

Further thoughts from committee to follow up on NEAFWA update:

Consider how to incorporate marine species in the NE synthesis:

- USFWS and NMFS- i.e. At Sturgeon- for marine species- recent stock assessment

- Consistent text and important to make a recommendation-  get NOAA

- Use Alison’s list?  # States listed them, # marine species listed? Mid Atlantic Regional Coastal (Ocean Planning =MARCO), Atlantic Fish Habitat Plan,

Steve Fuller recapped the status of the Species and Habitat data as follow up from NEAFWA meeting

- He will follow up w committee for review of data

- He’s collated responses from TNC and NatureServe data quality assessments

- July delivery of recommendations on species modeling/planning approach for committee review

- How to treat data/mapping issues need to be further discussed- will set up a July meeting

- Habitat Guides and draft Geospatial analysis will be delivered in September

Deadlines

- List of regional tools and actions: March 2013- completed

- Draft Synthesis Document 1: July 2013

- Draft 2: September 2013

- Final: December 2013

Review of synthesis pieces drafted to date

Suggestions for next review:  Most folks prefer individual review:

- Individual review- Kevin, Cathy, Becky, Charlie, Merry

- Possible small group editing sessions- Dee, Dianna

- Discuss at next meeting in July

Future Meeting info:

June 4-6th NCTC

Team mtg w TNC week of June 10th

July- will set up a committee follow up mtg or webex to review species and habitat data/analysis

September- 2nd or 3rd week in Sept NY meeting for NEFWDC- TBA

Discussion and next steps

Next Monthly call-   May 21st   1 pm – please put on your calendar