Table 1.  LCC Annual Process for Assessing Science Needs and Selecting Projects 		NEAFWA RCN Annual Process

| Date(s) | LCC Event | LCC Decision or Process |  | NEAFWA Event | NEAFWA Decision or Process |
| --- | --- | --- | --- | --- | --- |
| October | October LCC Technical Committee Meeting/Call | Recommendations on Projects for LCC Funding |  | NEWA/NEFA Meeting | Approve RCN Recommendations |
|  |  | Recommendations on CSC Needs |  |  |  |
| November | November LCC Steering Committee meeting | Funding Decisions on LCC Projects (including RCN projects for LCC support) |  | NEAFWA Directors Meeting | Final Decisions on RCN Projects |
|  |  |  |  |  | Approve Modification to Priority Topics for RFP |
| December |  | Notify Applicants/Announce Funding Decisions |  |  |  |
| January-February |  | Request Input on Science Needs to Partners |  |  | RCN Request for Proposals |
|  | LCC Steering Committee Conf. Call | Additional Decisions on Projects (as needed) |  |  |  |
| March | Technical Committee Call/Meeting | Develop Recommendations on Science Needs |  |  | RCN Proposals due |
| April | Steering Committee meeting at Northeast F&W Conference | Approval of Science Needs (including RCN topics that LCC could support); Additional decisions on projects (as needed) |  | Directors Meeting at Northeast F&W Conference | Select Priority RCN Topics for Following Year |
|  | Northeast F&W Conference | Presentations on completed LCC Projects |  | Northeast F&W Conference | Presentations on completed RCN Projects |
|  |  |  |  |  | Provide RCN proposals to tech. review teams |
| May-June |  | Assess need for RFP or direct contracts |  |  | Technical review scores due |
|  |  | Issue targeted RFP if needed |  |  |  |
| July | Technical Committee Call/Meeting | Review of Proposals, recommendations on initial science projects, identification of need for further work on proposals |  |  | Proposals reviewed and scored by states |
| August | LCC Steering Committee Conf. Call | Decisions on initial projects (as needed) |  |  |  |
| September |  | Revision of proposals (as needed); input from Northeast Fish and Wildlife Diversity Technical Committee |  | NE F&W Diversity Tech. Com. | Recommendations on RCN projects |